## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | [6 empty] | 2018-12-03
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
2023-01-01 | Project Charter | Leon W | 2018-12-03 | 3/15/18 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
2001-01-01 | Project Charter Revisions | Kylie R | 3/15/18 | 3/16/18 | 1 | 100% | bar: WEEK 2 W
2023-02-01 | Research | Pete S | 3/15/18 | 3/21/18 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
2023-03-01 | Projections | Steve L | 3/16/18 | 3/22/18 | 6 | 40% | bar: WEEK 2 R to WEEK 3 R
2023-04-01 | Stakeholders | Allen W | 3/18/18 | 3/22/18 | 4 | 70% | bar: WEEK 3 M to WEEK 3 R
2023-05-01 | Guidelines | Malik M | 3/19/18 | 3/22/18 | 3 | 60% | bar: WEEK 3 T to WEEK 3 R
2023-06-01 | Project Initiation | Malik M | 3/23/18 | 3/23/18 | 0 | 50% | bar: WEEK 3 F
2 | Project Definition and Planning
2023-01-02 | Scope and Goal Setting | Steve L | 3/24/18 | 3/28/18 | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
2023-02-02 | Budget | Allen W | 3/29/18 | 2018-02-04 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2023-03-02 | Communication Plan | Malik M |  |  | 0 | 0%
2023-04-02 | Risk Management | Malik M |  |  | 0 | 0%
3 | Project Conception and Initiation
2023-01-03 | Status and Tracking | Pete S |  |  | 0 | 0%
2023-02-03 | KPIs | Leon W |  |  | 0 | 0%
2001-02-03 | Monitoring | Kylie R |  |  | 0 | 0%
2002-02-03 | Forecasts | Kylie R |  |  | 0 | 0%
2023-03-03 | Project Updates | Pete S |  |  | 0 | 0%
2001-03-03 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Project Performance / Monitoring
2023-01-04 | Project Objectives | Steve L |  |  | 0 | 0%
2023-02-04 | Quality Deliverables | Allen W |  |  | 0 | 0%
2023-03-04 | Effort and Cost Tracking | Malik M |  |  | 0 | 0%
2023-04-04 | Project Performance | Malik M |  |  | 0 | 0%